## Progress by Feature
Epic | Feature | Total Tasks | Completed | Remaining | % Complete | Est Days (Total) | Est Days (Done) | Est Days (Remaining) | Status
Activity & Staff
Activity & Staff | Activity Sesion Instructor | 3 | 2 | 1 | 66.67% | 7 | 4 | 3 | 🔄 In Progress
Activity & Staff | Activity Creation & Management (Field Update) | 1 | 0 | 1 | 0% | 1.5 | 0 | 1.5 | 📋 Not Started
Activity & Staff | Assign Staff to Activity | 1 | 0 | 1 | 0% | 1 | 0 | 1 | 📋 Not Started
Activity & Staff | Activity Session Scheduling | 1 | 0 | 1 | 0% | 1.5 | 0 | 1.5 | 📋 Not Started
Activity & Staff | Activity List (filter by center) | 4 | 0 | 4 | 0% | 2 | 0 | 2 | 📋 Not Started
Activity & Staff | Activity Participant List | 4 | 0 | 4 | 0% | 2.5 | 0 | 2.5 | 📋 Not Started
Activity & Staff | Activity Participant Registration | 3 | 0 | 3 | 0% | 2.5 | 0 | 2.5 | 📋 Not Started
Activity & Staff | Marking Attendance (Time, Notes, Mood, Photos, Karya) | 6 | 0 | 6 | 0% | 11.5 | 0 | 11.5 | 🔄 In Progress
Activity & Staff | Activity Dashboard (overview, data summary) | 2 | 0 | 2 | 0% | 6.5 | 0 | 6.5 | 📋 Not Started
Activity & Staff | Activity Scoring (Health Index) | 2 | 0 | 2 | 0% | 1 | 0 | 1 | 📋 Not Started
Activity & Staff | Activity Adhoc | 3 | 0 | 3 | 0% | 4 | 0 | 4 | 📋 Not Started
Activity & Staff | Activity Listing (filter by Center) for User | 3 | 0 | 3 | 0% | 3.5 | 0 | 3.5 | 📋 Not Started
Activity & Staff | Activity Registration (By User) and Customer Service | 4 | 0 | 4 | 0% | 11 | 0 | 11 | 📋 Not Started
Activity & Staff | Activity History View | 3 | 0 | 3 | 0% | 3.5 | 0 | 3.5 | 📋 Not Started
Assessment
Assessment | Assessment Core (Shared) | 6 | 0 | 6 | 0% | 14 | 0 | 14 | 📋 Not Started
Assessment | Assessment UI Components (Shared) | 5 | 0 | 5 | 0% | 11 | 0 | 11 | 📋 Not Started
Assessment | FRAIL Scale | 2 | 0 | 2 | 0% | 1.5 | 0 | 1.5 | 📋 Not Started
Assessment | Barthel Index (Functional Status) | 2 | 0 | 2 | 0% | 1.5 | 0 | 1.5 | 📋 Not Started
Assessment | GDS-5 / GDS-15 (Depression Scale) | 3 | 0 | 3 | 0% | 3 | 0 | 3 | 📋 Not Started
Assessment | MNA (Mini Nutritional Assessment) | 3 | 0 | 3 | 0% | 3 | 0 | 3 | 📋 Not Started
Assessment | SARC-F + Neuromuscular Performance (Fall Risk) | 6 | 0 | 6 | 0% | 6.5 | 0 | 6.5 | 📋 Not Started
Assessment | Digit Span (Memory Test) | 4 | 0 | 4 | 0% | 5 | 0 | 5 | 📋 Not Started
Assessment | MoCA-INA (Cognitive Assessment) | 8 | 0 | 8 | 0% | 9.5 | 0 | 9.5 | 📋 Not Started
Assessment | Assessment Dashboard | 2 | 0 | 2 | 0% | 5 | 0 | 5 | 📋 Not Started
Assessment | Pre-Assessment (Staff Tablet) | 2 | 0 | 2 | 0% | 5 | 0 | 5 | 📋 Not Started
Core & Access
Core & Access | User Login (Email, Password) | 4 | 0 | 4 | 0% | 5 | 0 | 5 | 📋 Not Started
Core & Access | QR Generation for Login | 3 | 0 | 3 | 0% | 1.5 | 0 | 1.5 | 📋 Not Started
Core & Access | QR Login | 3 | 0 | 3 | 0% | 5 | 0 | 5 | 📋 Not Started
Core & Access | Session Token Management | 3 | 0 | 3 | 0% | 3.5 | 0 | 3.5 | 📋 Not Started
Core & Access | User Account Management | 4 | 0 | 4 | 0% | 3 | 0 | 3 | 📋 Not Started
Core & Access | Company Configuration | 1 | 0 | 1 | 0% | 1 | 0 | 1 | 📋 Not Started
Core & Access | Branch / Center Configuration | 2 | 0 | 2 | 0% | 1.5 | 0 | 1.5 | 📋 Not Started
Core & Access | Role-Based Permission | 3 | 0 | 3 | 0% | 2.5 | 0 | 2.5 | 📋 Not Started
Core & Access | Senior App Setup | 1 | 0 | 1 | 0% | 3 | 0 | 3 | 📋 Not Started
Finance
Finance | Income Transaction Recording | 1 | 0 | 1 | 0% | 2 | 0 | 2 | 📋 Not Started
Finance | Expense Transaction Recording | 1 | 0 | 1 | 0% | 2 | 0 | 2 | 📋 Not Started
Finance | Financial Journal View | 1 | 0 | 1 | 0% | 1.5 | 0 | 1.5 | 📋 Not Started
Finance | Chart of Accounts Setup | 1 | 0 | 1 | 0% | 2 | 0 | 2 | 📋 Not Started
Finance | General Ledger (Buku Besar) | 1 | 0 | 1 | 0% | 4 | 0 | 4 | 📋 Not Started
Finance | Profit & Loss Report | 1 | 0 | 1 | 0% | 4 | 0 | 4 | 📋 Not Started
Finance | Capital Injection / Owner Prive Recording | 1 | 0 | 1 | 0% | 2.5 | 0 | 2.5 | 📋 Not Started
Finance | Balance Sheet Report (Neraca) | 1 | 0 | 1 | 0% | 5 | 0 | 5 | 📋 Not Started
Health Measurement
Health Measurement | Health Measurement (Field and Form Update) | 4 | 2 | 2 | 50% | 8 | 3 | 5 | 🔄 In Progress
Health Measurement | Latest Health Measurement View on Profile | 1 | 0 | 1 | 0% | 1.5 | 0 | 1.5 | 📋 Not Started
Health Measurement | Health Measurement History | 3 | 0 | 3 | 0% | 3 | 0 | 3 | 📋 Not Started
Health Measurement | Health Station - Resident QR Selection | 3 | 0 | 3 | 0% | 6 | 0 | 6 | 📋 Not Started
Health Measurement | Health Station - Resident Manual Selection | 2 | 0 | 2 | 0% | 3.5 | 0 | 3.5 | 📋 Not Started
Health Measurement | Bluetooth Device Connection | 2 | 0 | 2 | 0% | 7.5 | 0 | 7.5 | 📋 Not Started
Health Measurement | Health Measurement via Device v1 (Oximeter, Thermometer, Tensimeter) | 4 | 0 | 4 | 0% | 8 | 0 | 8 | 📋 Not Started
Health Measurement | Measurement Dashboard | 3 | 0 | 3 | 0% | 8 | 0 | 8 | 📋 Not Started
Health Measurement | Measurement Sync to Backend | 2 | 0 | 2 | 0% | 6.5 | 0 | 6.5 | 📋 Not Started
Learning
Learning | Knowledge Management | 1 | 0 | 1 | 0% | 2 | 0 | 2 | 📋 Not Started
Learning | Learning Module Creation & Management | 1 | 0 | 1 | 0% | 2.5 | 0 | 2.5 | 📋 Not Started
Learning | Text Book (Senior App) | 5 | 0 | 5 | 0% | 8.5 | 0 | 8.5 | 📋 Not Started
Learning | Audiobook (Senior App) | 2 | 0 | 2 | 0% | 3.5 | 0 | 3.5 | 📋 Not Started
Member & Medical
Member & Medical | Member Profile | 3 | 2 | 1 | 66.67% | 3.5 | 2.5 | 1 | 🔄 In Progress
Member & Medical | Member | 2 | 1 | 1 | 50% | 1 | 0.5 | 0.5 | 🔄 In Progress
Member & Medical | NOK & Family Tree | 5 | 2 | 3 | 40% | 9.5 | 2.5 | 7 | 🔄 In Progress
Member & Medical | Medical Care Record (SOAP) | 3 | 1 | 2 | 33.33% | 6 | 2 | 4 | 🔄 In Progress
Member & Medical | Create Member (Minimal form) | 2 | 0 | 2 | 0% | 3.5 | 0 | 3.5 | 📋 Not Started
Member & Medical | Informed Consent Form | 4 | 0 | 4 | 0% | 8 | 0 | 8 | 📋 Not Started
Member & Medical | Medication Prescription | 3 | 0 | 3 | 0% | 2 | 0 | 2 | 📋 Not Started
Member & Medical | Medication Administration History | 5 | 0 | 5 | 0% | 3.5 | 0 | 3.5 | 📋 Not Started
Member & Medical | Additional Info | 3 | 0 | 3 | 0% | 2 | 0 | 2 | 📋 Not Started
Member & Medical | Attachments | 3 | 0 | 3 | 0% | 2 | 0 | 2 | 📋 Not Started
Member & Medical | Calendar | 4 | 0 | 4 | 0% | 3 | 0 | 3 | 📋 Not Started
Member & Medical | Careplan | 3 | 0 | 3 | 0% | 2 | 0 | 2 | 📋 Not Started
Member & Medical | Allergies | 3 | 0 | 3 | 0% | 2 | 0 | 2 | 📋 Not Started
Member & Medical | Meal and Foodplan | 5 | 0 | 5 | 0% | 7 | 0 | 7 | 📋 Not Started
RnD
RnD | Health Measurement via Device v2 (Scale Weight + Hand Grip) | 3 | 0 | 3 | 0% | 9 | 0 | 9 | 📋 Not Started
RnD | Cognitive Games | 2 | 0 | 2 | 0% | 10 | 0 | 10 | 📋 Not Started
RnD | Exercise Buddy (+New Exercise Movement) | 2 | 0 | 2 | 0% | 8 | 0 | 8 | 📋 Not Started
RnD | Letter Buddy (AI) | 2 | 0 | 2 | 0% | 8 | 0 | 8 | 📋 Not Started
RnD | Digital Pet (AI) | 2 | 0 | 2 | 0% | 12 | 0 | 12 | 📋 Not Started
RnD | Update AI Recommendation | 2 | 0 | 2 | 0% | 7 | 0 | 7 | 📋 Not Started
RnD | SPPB using Camera (ML Body Recognition) | 2 | 0 | 2 | 0% | 13 | 0 | 13 | 📋 Not Started
RnD | Wearable Health | 2 | 0 | 2 | 0% | 9 | 0 | 9 | 📋 Not Started

## Progress by Epic
Epic | Features | Total Tasks | Completed | Remaining | % Complete | Est Days (Total) | Est Days (Remaining) | Status
Member & Medical | 14 | 48 | 6 | 42 | 12.5% | 55 | 47.5 | 🔄 In Progress
Health Measurement | 9 | 24 | 2 | 22 | 8.333% | 52 | 49 | 🔄 In Progress
Activity & Staff | 14 | 40 | 2 | 38 | 5% | 59 | 55 | 🔄 In Progress
Core & Access | 9 | 24 | 0 | 24 | 0% | 26 | 26 | 📋 Not Started
Assessment | 11 | 43 | 0 | 43 | 0% | 65 | 65 | 📋 Not Started
Finance | 8 | 8 | 0 | 8 | 0% | 23 | 23 | 📋 Not Started
Learning | 4 | 9 | 0 | 9 | 0% | 16.5 | 16.5 | 📋 Not Started
RnD | 8 | 17 | 0 | 17 | 0% | 76 | 76 | 📋 Not Started

## Overall Summary
PROJECT PROGRESS SUMMARY
Generated: 25 Maret 2026
OVERALL
Total Tasks | 213
Completed | 10
In Progress | 3
To Do | 123
Backlog | 77
Overall Completion | 4.695%
Est Days (Total) | 372.5
Est Days (Remaining) | 358
BY PHASE
MVP Total | 136
MVP Completed | 10
MVP % Complete | 7.353%
Phase 2 Total | 77
Phase 2 Completed | 0
Phase 2 % Complete | 0%
TOP PROGRESS
Member Profile | 66.67%
Activity Sesion Instructor | 66.67%
Member | 50%
Health Measurement (Field and Form Update) | 50%
NOK & Family Tree | 40%